## mlb11
Date | Objectives
2020-11-06 | set goals and have a proposal
2020-11-07 | hand in the proposal
2020-11-10 | tidy the data, preliminary work
2020-11-12 | meet with TA, make correction
2020-11-20 | have tidy data, basic frames of the website
2020-11-25 | started to write the final report
2020-11-29 | have group meeting, complete report and the website
2020-12-04 | polise final report, screencast, webpages
2020-12-08 | do peer assessment
2020-12-10 | in-class discussion of projects